## Action Log
UCSC Baskin Project - Action Log of Open Items
Date Added | Item No. | Item | Owner | Date Due | Dependency | Actual Date Done | Status | Value Message Statement | Deliverable Format
2018-02-21 | 14 | Identify IR light source | Kevin / Jan - Rob Ordered, arrive by 3/2 | 2018-02-23 | Delivery |  | Open
2018-02-21 | 15 | Setup for rainy conditions | Kevin | 2018-02-28 | School |  | Open
2018-02-21 | 16 | Camera filters to simulate darkness gradation | Kevin | 2018-02-23 |  |  | Open
2018-02-21 | 17 | Investigate feasibility of license plate feature network to match entrance / exit images (instead of exact number match). Some work during week 2/21 to 2/28 | UCSC team | 2018-02-28 |  |  | Open
2018-02-28 | 18 | Rob to provide a list of reading / research to team to prep for shifting to contaminant detection work starting next week. | Rob | 2018-03-02 |  |  | Open
2018-02-28 | 19 | Find what, if any, reporting Atollogy should do back to team's professor. | Team | 2018-03-01 |  |  | Open
UCSC Baskin Project - Action Log of Closed Items
Date Added | Item No. | Item | Owner | Date Due |  | Actual Date Done | Status | Value Message Statement | Deliverable Format
2018-01-31 | 1 | Set Up One Drive as Document Repository | Duck Ha | 2018-01-31 |  | 2018-01-31 | Done
2018-01-31 | 2 | Provide Link to Discord IM | Kevin | 2018-01-31 |  | 2018-01-31 | Done
2018-01-31 | 3 | Provide Documenation for Motion Camera | Duck Ha | 2018-01-31 |  | 2018-01-31 | Done
2018-01-31 | 4 | Provide UC Team with Link for Image Capture | Duck Ha & Frank | 2018-01-31 |  | 2018-01-31 | Done
2018-01-31 | 5 | Upload Cemex Photos - Day & Early AM | Rob | 2018-02-01 | N/A | 2018-02-02 | Done
2018-01-31 | 6 | Provide UC Team with Direction/Instruction on how to Config WiFi in PI | Duck Ha & Frank | 2018-02-01 | N/A | 2018-02-07 | Done
2018-01-31 | 7 | Investigate delay in booting up Pi's | Duck Ha & Frank | 2018-02-05 | N/A | 2018-02-07 | Done
2018-02-14 | 12 | Send team instructions for using the alignment utiliity | Rob | 2018-02-15 |  | 2018-02-14 | Done
2018-02-07 | 8 | Check on calendar and mid term issues | Kevin | 2018-02-09 | N/A | 2018-02-14 | Done
2018-02-07 | 9 | Connecting to school network | Kevin | 2018-02-14 | School | 2018-02-17 | Done
2018-02-07 | 10 | Determine distribution of work - 2 teams | Kevin | 2018-02-14 |  | 2018-02-14 | Done
2018-02-14 | 11 | Get a IR camera and Mobile Hot Spot spare battery pack and 3 WizGear & USB cords and an Extra Web cam to Apollo for Delivery | Rob | 2018-02-17 |  | 2018-02-17 | Done
2018-02-14 | 13 | Jan to check w Todd on if they the alignment web server is running. | Jan (completed by UC team) | 2018-02-17 |  | 2018-02-17 | Done

## Meeting Log
Meeting Log
Date | Meeting Name | Meeting Host | Meeting Duration | UCSC Attendees | Atollogy Attendees | Discussions/Decisions
2018-01-31 | Weekly Status Call | Tony Tarantino | 40 Minutes | Cesar, Arindam,David, Kevin, An, Eric | Rob, Frank, Duck Ha, Tony | See Action Log
2018-02-07 | Weekly Status Call | Tony Tarantino | 36 Minutes | Cesar, Arindam,David, Kevin, An, Eric | Jan, Duck Ha, Tony. Rob | See Action Log
2018-02-14 | Weekly Status Call | Rob S |  | Cesar, Arindam,David, Kevin, An, Eric | Rob, Jan | Team using a few different appraoches (Open CV, Open ALPR and Open ALPR Cloud) Open versions seem to be less accurate. They recognize the License plae but get charactgers wrong, and in an indoor environment they sometimes they see seomthing ELSE as the license plate. USB Camera seems to be better than the Pi Camera. On the Pi, taking about 2 seconds.

## 4 Wk Agenda
Week 1 - Feb 5
Finalize Group Work Structure, Start Architecture Design
Acquire Test Images from different settings
• Combination of the following scenarios: Daylight, Evening, Early morning, Outdoor/Indoor, Fog, Rain
Week 2 - Feb 12
Finalize Architecture and design
Start working on the components
Week 3 - Feb 19
Continue to work on finishing the components
Week 4 - Feb 26
Demonstrate the prototype of successfully getting the license plate numbers from the images acquired
3:00 Session on Mar 2 over Zoom (to be recorded)
Week 5 - Mar 5
Start work on Contaminant detection
Week 6 - Mar 12
Design Experiements to perform at True Leaf Food Processing Facility in April
Week 7 - Mar 18
Finals week
Week 8 - Mar 25
Spring Break

## Team Members
UCSC Team
Name | Date Added | Role | Cell # | Emai
An Tran |  |  |  | anngtran@ucsc.edu
Arindam Sarma |  |  |  | asarma@ucsc.edu
Cesar Neri |  |  |  | ceneri@ucsc.edu
David Munoz |  |  |  | dmunoz5@ucsc.edu
Eric Su |  |  |  | eysu@ucsc.edu
Kevin Ajili |  |  |  | kajili@ucsc.edu
Prof. Richard Jullig |  | Faculty Sponsor | (408) 621-1608 | rjullig@ucsc.edu
Atollogy Team
Name |  | Role | Cell # | Email
Duck Ha Hwang |  | Technical Advisor | 424-320-1150 | duck@atollogy.com
Frank Poon |  | Project Advisor | 214-476-8712 | frank@atollogy.com
Jan Jannik |  | Technical Mentor |  | jan@atollogy.com
Rob Schoenthaler |  | CEO & Project Executive Sponsor | 323-314-3414 | rob@atollogy.com
Tony Tarantino |  | Program Manager | 562-818-3275 | tony@atollogy.com

## Communication Plan
Project Communication Plan
Item | Description | Link / Email | Phone
Weekly Project Team Call | Wednesday 6pm PST via Zoom | https://zoom.us/j/162660132
Ad Hoc IM via Discord | Discord | https://discord.gg/wmTGVxY
Document Repository | Office 360 - One Drive | https://atollogy-my.sharepoint.com/:f:/p/rob/Eryq7cPb1TFLuOU23CaklU0BEuk_6yeCkACUCGHG7ST3JQ?e=01jw0o
Atollogy Primary Contact | Tony Tarantino | tony@atollogy.com | 562-818-3275
UCSC Primary Contact | Kevin Ajili | kajili@ucsc.edu

## Out of Office Log
Out of Office Log
Date Entered | Team Member | Reason | From Date | To Date | Back Up
2018-01-31 | Jan | PTO | 2018-01-31 | 2018-01-31 | Frank & Duck Ha
2018-02-14 | Duck Ha | PTO | 2018-02-10